## Zones
Zone ID | Zone Name | Type | Dimensions | Location (relative description) | Power Plan | Comms | Primary Sensors | Actuators / Control | Install Phase | Status | Notes
bed_01 | Raised Bed 1 | Soil bed | 6x3 ft | TBD: assign in clockwise order around garden cluster | 24V trunk (preferred) or battery | Wi‑Fi MQTT (wired) / ESP‑NOW (battery) | Soil moisture (x2), soil temp (x1), light (optional) | None (monitoring only) | Phase 3 | Planned | Use 2 probes per bed; average/median for control
bed_02 | Raised Bed 2 | Soil bed | 6x3 ft | TBD: assign in clockwise order around garden cluster | 24V trunk (preferred) or battery | Wi‑Fi MQTT (wired) / ESP‑NOW (battery) | Soil moisture (x2), soil temp (x1), light (optional) | None (monitoring only) | Phase 3 | Planned | Use 2 probes per bed; average/median for control
bed_03 | Raised Bed 3 | Soil bed | 6x3 ft | TBD: assign in clockwise order around garden cluster | 24V trunk (preferred) or battery | Wi‑Fi MQTT (wired) / ESP‑NOW (battery) | Soil moisture (x2), soil temp (x1), light (optional) | None (monitoring only) | Phase 3 | Planned | Use 2 probes per bed; average/median for control
bed_04 | Raised Bed 4 | Soil bed | 6x3 ft | TBD: assign in clockwise order around garden cluster | 24V trunk (preferred) or battery | Wi‑Fi MQTT (wired) / ESP‑NOW (battery) | Soil moisture (x2), soil temp (x1), light (optional) | None (monitoring only) | Phase 3 | Planned | Use 2 probes per bed; average/median for control
bed_05 | Raised Bed 5 | Soil bed | 6x3 ft | TBD: assign in clockwise order around garden cluster | 24V trunk (preferred) or battery | Wi‑Fi MQTT (wired) / ESP‑NOW (battery) | Soil moisture (x2), soil temp (x1), light (optional) | None (monitoring only) | Phase 3 | Planned | Use 2 probes per bed; average/median for control
bed_06 | Raised Bed 6 | Soil bed | 6x3 ft | TBD: assign in clockwise order around garden cluster | 24V trunk (preferred) or battery | Wi‑Fi MQTT (wired) / ESP‑NOW (battery) | Soil moisture (x2), soil temp (x1), light (optional) | None (monitoring only) | Phase 3 | Planned | Use 2 probes per bed; average/median for control
bed_07 | Raised Bed 7 | Soil bed | 6x3 ft | TBD: assign in clockwise order around garden cluster | 24V trunk (preferred) or battery | Wi‑Fi MQTT (wired) / ESP‑NOW (battery) | Soil moisture (x2), soil temp (x1), light (optional) | None (monitoring only) | Phase 3 | Planned | Use 2 probes per bed; average/median for control
bed_08 | Raised Bed 8 | Soil bed | 6x3 ft | TBD: assign in clockwise order around garden cluster | 24V trunk (preferred) or battery | Wi‑Fi MQTT (wired) / ESP‑NOW (battery) | Soil moisture (x2), soil temp (x1), light (optional) | None (monitoring only) | Phase 3 | Planned | Use 2 probes per bed; average/median for control
longbed_a | Long Bed A (24x3) | Soil bed | 24x3 ft (left half) | TBD: left half of 24x3 bed | 24V trunk | Wi‑Fi MQTT | Soil moisture (x2), soil temp (x1) | Valve optional (future) | Phase 3 | Planned | Split for sensing even if watering is single valve
longbed_b | Long Bed B (24x3) | Soil bed | 24x3 ft (right half) | TBD: right half of 24x3 bed | 24V trunk | Wi‑Fi MQTT | Soil moisture (x2), soil temp (x1) | Valve optional (future) | Phase 3 | Planned
bucket_sun | Planter Buckets (Full Sun) | Containers | Varies | TBD: buckets in full sun area | Battery (initial) or 24V spur | ESP‑NOW (battery) / Wi‑Fi MQTT (wired) | Representative soil moisture, soil temp | None | Phase 4 | Planned | Group containers by exposure & watering behavior
bucket_shade | Planter Buckets (Partial Shade) | Containers | Varies | TBD: buckets in partial shade area | Battery (initial) or 24V spur | ESP‑NOW (battery) / Wi‑Fi MQTT (wired) | Representative soil moisture, soil temp | None | Phase 4 | Planned
raspberry | Raspberry Patch (In-ground) | In-ground bed | TBD | TBD: at-grade raspberry bed | Battery or 24V spur | ESP‑NOW (battery) / Wi‑Fi MQTT (wired) | Soil moisture (2 depths), soil temp | Valve optional (future) | Phase 4 | Planned | In-ground behaves differently than raised beds; consider deeper probe
gh_climate | Greenhouse Climate | Greenhouse | 12 ft diameter dome | Greenhouse interior (mount sensors at canopy height) | Mains/24V | Wi‑Fi MQTT | Air temp+RH (SHT3x), light (lux), optional 2nd temp+RH | Fans, vents (future) | Phase 1 | Planned | Use VPD/dew point for control; add stratification sensor later
hydro_ebbflow_01 | Hydro Ebb & Flow System 01 | Hydroponics | TBD | Greenhouse (near ebb & flow reservoir) | Mains/24V | Wi‑Fi MQTT | Water temp, level (2 floats), optional flow, air temp+RH | Pump, valve(s), alarms | Phase 2 | Planned | Local safety: low-low cutoff, max runtime, flow expected check
hydro_nft_01 | Hydro NFT System 01 | Hydroponics | TBD | Greenhouse (near NFT reservoir/manifold) | Mains/24V | Wi‑Fi MQTT | Flow-present, water temp, reservoir level, optional EC/pH | Alarms/indicator only (no pump control planned) | Phase 2 | Planned | Focus on detecting flow loss & overheating
gateway_01 | ESP‑NOW Gateway | Infrastructure | N/A | Greenhouse (mounted high ~5–6 ft) | Mains/24V | Wi‑Fi MQTT + ESP‑NOW | N/A | Bridges ESP‑NOW → MQTT | Phase 1 | Planned | Only needed if you keep battery ESP‑NOW soil nodes

## Placement Notes
How to use this sheet
1) Walk the garden and assign each 6x3 bed a stable ID (bed_01..bed_08) in a clockwise order starting near the greenhouse.
2) Fill in the Location column with a clear phrase (e.g., 'North row, closest to trellis, 2nd bed from gate').
3) If you wire 24V, note the trunk route and spur length; if battery, note target battery type and service interval.
4) Keep sensors consistent per zone so Mycodo dashboards stay standardized.
Suggested trunk route idea (text-only placeholder): run 24V along trellis path, loop around raised beds, then into greenhouse.